## Slide 1
WEB CREATION WORKFLOW
Week 1: Web Logo & Brand Identity
A weekly task plan for participants to build a professional web identity before moving to AI prompts, Stitch, Figma, frontend, backend, and WordPress options.
Logo
Colors
Fonts
Voice
AI Marketing Team Database • Web Creation Training
Week 1

## Slide 2
Full Web Path: From identity to launch
Each part becomes one week of participant tasks.
1
Logo & Identity
Brand base
2
AI Prompt + Stitch
First concept
3
Figma
UI/UX prototype
4
Frontend
Google AI Studio
5
Backend
Google AI Studio / Antigravity
6
WordPress Option
CMS solution
7
Launch Plan
Final delivery
Focus now: Week 1 creates the visual identity kit that every next week will use.
AI Marketing Team Database • Web Creation Training
Week 1

## Slide 3
Week 1 Objectives
Participants turn a business idea into a clear visual identity.
1. Understand the business
Business name & story
Products / services
Target audience
Competitors reference
2. Define the identity
Logo direction
Color palette
Fonts and typography
Tone of voice
3. Prepare web assets
Logo files
Brand mini-guide
Hero message
Visual examples for AI
🏢
🎨
🧩
Result: every participant finishes Week 1 with a strong brand base ready for AI website generation.
AI Marketing Team Database • Web Creation Training
Week 1

## Slide 4
Week 1 Task Plan
A simple 5-day rhythm for the first web part.
Day 1
Business brief
Fill the business profile: identity, products, prices, audience, story.
Day 2
Moodboard
Collect 10 visual references: logos, colors, fonts, competitors, web styles.
Day 3
Logo ideas
Generate 3 logo concepts, choose one direction, write the logic behind it.
Day 4
Identity kit
Finalize colors, fonts, tone of voice, button style, and homepage visual mood.
Day 5
Presentation
Present the identity kit and prepare files for Week 2 prompt generation.
AI Marketing Team Database • Web Creation Training
Week 1

## Slide 5
Tool Workflow for Week 1
Where each participant creates and stores the brand identity.
🗂️
Database
Google Drive / Notebook
Collect brand data and references
✨
AI Prompt
Gemini / ChatGPT
Generate logo direction and identity text
🧵
Stitch
stitch.google.com
Try first web layout ideas
🎛️
Figma
figma.com
Organize UI colors, fonts, and components
Important: Week 1 is not coding yet. It is the identity foundation that guides every AI and design decision.
AI Marketing Team Database • Web Creation Training
Week 1

## Slide 6
Participant Deliverables
What each participant must submit at the end of Week 1.
Identity mini-guide
Logo selected direction
Primary and secondary colors
2 fonts: title + body
Tone of voice: 5 keywords
Website content base
Hero title and subtitle
About text short version
Products / services list
Target audience statement
Asset folder
Logo file
Moodboard images
Competitor screenshots
AI prompt draft
Evaluation: clarity, consistency, creativity, and readiness for Week 2 AI prompt generation.
AI Marketing Team Database • Web Creation Training
Week 1

## Slide 7
Handoff to Week 2
The identity becomes a strong prompt for web generation.
Week 1 output
Logo + colors + fonts + voice + content base
Week 2 task
Create a complete AI website prompt and test first layout in Stitch
Final direction
Choose the best concept before moving to Figma and Google AI Studio
Next slide deck: Week 2 — AI Prompt Form + Stitch.Google.com website concept.
AI Marketing Team Database • Web Creation Training
Week 1